## GanttChart
Image Search Engine
|  | October |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
TASK | PREDECESSOR | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3
Initial work plan | bar: October Wk3 to October Wk4
Create project/ setup classes | bar: November Wk1
Create GUI | bar: November Wk2
User image input | bar: November Wk3
Clear input | bar: November Wk3
Colour distance measurement | bar: November Wk4 to December Wk2
Shape distance measurement | bar: December Wk3 to January Wk1
Texture distance measurement | bar: January Wk2 to January Wk4
Iterate through gallery | bar: February Wk1
Calculate best matched images | bar: February Wk2
Display images | bar: February Wk3
Note on A3: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C3: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.